ISURA FASHION

INCEPTION REPORT

Development of the Isura Fashion Fashion Ecommerce Platform

| Document ID | ISF-INC-2026-001 |
| --- | --- |
| Project | Isura Fashion — Fashion Ecommerce Platform |
| Client | Isura Fashion ¦ Kigali, Rwanda |
| Programme | SPEDO501 · Perform DevOps · Year 3 SPE |
| School / cohort | Rwanda Coding Academy · 2026–2027 |
| Prepared by | Cyuzuzo · Year 3 Software Programming & Embedded Systems |
| Version / date | v1.0 — Initial baseline · 26 September 2026 |

Related documents: ISF-SRS-2026-001 · ISF-UAT-2026-001

STATUS: BASELINED — academic project draft

# Table of Contents

1 Executive summary

2 Project background and programme context

3 Scope of work

4 Project organisation and team

5 Development methodology (including SRS/UAT binding)

6 Technical architecture overview

7 Project work plan, Gantt and milestones

8 Effort and resources

9 Communication and reporting

10 Risk register

11 Quality and UAT approach

12 Assumptions and dependencies

13 Immediate next steps

Annex A Gantt · Annex B Document set

# 1. Executive summary

This Inception Report starts the Isura Fashion SPEDO501 project. It binds the SRS requirements and UAT acceptance approach to a practical development plan, milestones, risks, resources and governance. The project delivers a web storefront, REST API, database, payment adapter, containers, CI/CD and observability.

# 2. Project background and programme context

SPEDO501 requires trainees to configure an environment, execute tests, monitor logs and prepare documentation against a running scenario. Isura Fashion is the selected fashion ecommerce scenario.

| Party | Representative | Role |
| --- | --- | --- |
| Isura Fashion | Product Owner / SME | Client; UAT lead; release authority |
| Year 3 SPE student | Cyuzuzo | Build, test, operate, document |
| RCA trainer | Technical authority / QA lead | Baseline documents and assess |
| RTB / RCA | Awarding body | Summative assessment |

# 3. Scope of work

| Component | Description | SRS / UAT | Milestone |
| --- | --- | --- | --- |
| Web storefront | React catalogue, filters, cart, login, checkout, wishlist | UC-IF-01..10 | M2–M3 |
| REST API + DB | Auth, catalogue, cart, orders, payment adapter, admin | FR-* | M2–M3 |
| Payment adapter | MoMo/Card stub: success, decline, 45s timeout | UC-IF-08 / CO-008..012 | M3 |
| Containers + K8s | Dockerfiles, Compose, Deployment/Service, scale 3→5 | FR-DEV-01..02 | M2 |
| CI/CD | Build, test, deploy on push | FR-DEV-03 | M2 |
| Testware | Plan, EP/BVA, 12+ cases, RTM, performance/security | UAT pack | M3 |
| Observability | JSON logs, Prometheus, Loki, Grafana, 2 alerts | FR-OBS / NF | M4 |
| LO4 reports | Findings, UAT report, metrics, recommendations | LO4 | M5 |

Out of scope: native mobile apps; payment gateway internals/live charges; multi-vendor marketplace; WMS/ERP; live production customer data; public launch without trainer approval.

# 4. Project organisation and team

| Role | Who | Accountability |
| --- | --- | --- |
| Product Owner | Isura Fashion | Prioritise; accept SRS; UAT; sign-off |
| Tech lead / trainer | RCA trainer | Baseline; defects; assessment |
| Developer | Cyuzuzo | Frontend/backend integration, tests, documentation |
| DevOps | Project role | Docker, K8s, pipeline, Grafana, alerts |
| QA / test lead | Project role | RTM, test execution, UAT facilitation |

# 5. Development methodology

## 5.1 Sprint structure (mapped to the scheme of work)

| Sprint | Weeks | Focus | Review gate |
| --- | --- | --- | --- |
| S0 Inception | W1–W2 | Report, SRS, UAT pack, repo | M1 accepted |
| S1 Environment | W2–W6 | Docker, K8s, Git, CI/CD | M2 services + pipeline |
| S2 Storefront core | W3–W10 | Auth, catalogue, cart, wishlist, checkout | PO demo |
| S3 Test & UAT | W8–W13 | EP/BVA, tests, performance, security, UAT | M3 executed pack |
| S4 Observe | W12–W15 | Logs, dashboards, alerts | M4 evidence |
| S5 Close | W16–W18 | Findings, UAT, recommendations, demo | M5 sign-off |
| Exam | W19 | Written + practical | Module exam |

## 5.2 Ceremonies and artifacts

Stand-up each lab day: blockers, commits and failing tests.

Weekly review: demo completed use cases against the SRS.

Milestone review: Product Owner + trainer.

Every UAT Fail receives a Defect ID.

RTM maps every High requirement to a UAT ID before closure.

Change requests are written and impact-assessed; no silent scope additions.

## 5.3 How this report, the SRS and UAT fit together

| V-Model left arm | Right arm / test | Governing document |
| --- | --- | --- |
| Requirements gathering | Acceptance tests / UAT | SRS §5 + UAT |
| System design | System/E2E tests + JMeter | SRS §3, §10 + UAT NF |
| Module design | API + DB + adapter integration | SRS §6, §7 |
| Unit design | JUnit/RTL/TDD tests | SRS functional requirements |
| Coding | Pipeline test before deploy | FR-DEV-03 |

# 6. Technical architecture overview

Figure 6.1 — Architecture overview. UAT executes against the staging/UAT environment.

# 7. Project work plan and schedule

| Week | Dates | Tasks | Deliverable / gate |
| --- | --- | --- | --- |
| 1 | 26 Sep–2 Oct | Kick-off; requirements; draft SRS/UAT | M1 draft |
| 2 | 3–9 Oct | Baseline docs; Docker | M1 |
| 3 | 10–16 Oct | Compose services | Healthy compose |
| 4 | 17–23 Oct | K8s Deployment/Service; scale | kubectl evidence |
| 5 | 24–30 Oct | Git workflow; hardening | PR history |
| 6 | 31 Oct–6 Nov | CI/CD Build-Test-Deploy | M2 |
| 7 | 7–13 Nov | LO1 CAT | CAT evidence |
| 8 | 14–20 Nov | V-Model/STLC | Requirements register |
| 9 | 21–27 Nov | Test plan; RTM | rtm.csv |
| 10 | 28 Nov–4 Dec | EP/BVA; decision tables; TDD | Lab 3/3A |
| 11 | 5–11 Dec | Execute; regression; JMeter; security | Lab 4 |
| 12 | 12–18 Dec | UAT session 1; JSON logging | M3 |
| 13 | 19–25 Dec | Grafana golden signals | Dashboard |
| 14 | 26 Dec–1 Jan | Loki; dashboard completion | M4 prep |
| 15 | 2–8 Jan | Alert rules | Evidence |
| 16 | 9–15 Jan | Findings + UAT 2 | UAT report |
| 17 | 16–22 Jan | Recommendations; 5 Whys | LO4 pack |
| 18 | 23–29 Jan | Integrated demo | M5 |
| 19 | 30 Jan | Exam | Summative |

## 7.1 Milestone acceptance criteria

| Milestone | Trigger | Evidence |
| --- | --- | --- |
| M1 | Inception accepted; SRS baselined; UAT issued | Signed report + SRS + UAT |
| M2 | Containers/K8s healthy; pipeline green | Lab 1–2 |
| M3 | High UAT cases executed; no untested High FR | UAT Dashboard + RTM |
| M4 | Four golden signals + two alerts | Grafana screenshots |
| M5 | UAT verdict; LO4 reports; demo | Sign-off + findings |

# 8. Effort and resources

| Resource | Allocation | Notes |
| --- | --- | --- |
| Contact hours | 80 h | SPEDO501 structure |
| LO1 | 30 h | Environment |
| LO2 | 20 h | Testing |
| LO3 | 20 h | Observability |
| LO4 | 10 h | Documentation/UAT |
| Compute | Lab PCs + AWS Free Tier/kind/minikube | No production spend without approval |
| Tools | GitHub/GitLab, Docker, K8s, JMeter/Gatling, Grafana, Issues/Jira | Project tools |
| UAT | ≥2 shoppers + 1 admin + Product Owner | Prefer independent participants |

# 9. Communication and reporting

| Channel | Frequency | Audience | Owner |
| --- | --- | --- | --- |
| Stand-up | Each lab day | Project | Developer |
| Weekly demo | Friday | Trainer + PO | Team lead |
| Defect SLA | 24h to triage | QA/developer | QA lead |
| Milestone review | End M1–M5 | PO + trainer | Trainer |
| Escalation | Same day if UAT blocked | Trainer | Team lead |

# 10. Risk register

| ID | Risk | L | I | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | UAT environment not smoke-tested | M | H | Mandatory smoke checklist |
| R02 | Payment timeout after Paid creates inconsistency | M | H | Explicit timeout requirement + CO-011 |
| R03 | Native-app/live-payment scope creep | M | H | Out-of-scope list in all documents |
| R04 | Only E2E tests, no unit tests | H | M | TDD + pipeline test stage |
| R05 | Wishlist persistence not tested | M | H | Dedicated UAT case + RTM check |
| R06 | Cluster/Docker unavailable | M | M | Week 2 dry-run; Compose fallback |
| R07 | Developers act as UAT signers | H | M | Independent PO/shoppers where possible |
| R08 | Sensitive data in logs | L | H | SEC rules + log review |

# 11. Quality and UAT approach

First-time shopper can register, browse, apply ISURA2026 and complete successful MoMo checkout unaided.

Gold customer receives free shipping below 50,000 RWF when Gold tier applies.

MoMo timeout never leaves order Paid; recoverable PaymentTimedOut state shown.

Admin can publish a product and ship a Paid order using quick-start guidance.

Record task success rate, time-on-task and 1–5 satisfaction.

Entry: M2 environment, SRS baseline, UAT pack, seed data and green smoke test. Exit: High UAT cases Pass or formally waived, no open Critical defects, and Product Owner/QA sign-off.

# 12. Assumptions and dependencies

| ID | Assumption / dependency | Owner | Needed by |
| --- | --- | --- | --- |
| A01 | Docker/Git and cluster available | Trainer/RCA IT | Week 2 |
| A02 | PO available for demos/UAT | Trainer | Week 8 |
| A03 | Payment stub controllable | Developer | Week 10 |
| A04 | SRS/UAT remain version-locked | QA | Ongoing |
| A05 | No real customer data | All | Ongoing |
| A06 | Report accepted within five working days | PO + trainer | Week 2 |

# 13. Immediate next steps

| # | Action | Owner | Deadline |
| --- | --- | --- | --- |
| 1 | Accept Inception Report | PO + trainer | 2 Oct 2026 |
| 2 | Baseline SRS | Developer + trainer | 2 Oct 2026 |
| 3 | Issue UAT pack with Not Executed statuses | QA | 2 Oct 2026 |
| 4 | Create Git repo, board and RTM | Developer | 30 Sep 2026 |
| 5 | Schedule UAT sessions | QA | 20 Nov 2026 |
| 6 | Confirm Docker/K8s availability | Trainer | 30 Sep 2026 |

# Annex A — Gantt overview

The work-plan table in §7 is the Gantt baseline. M1–M5 mark the five internal quality gates; UAT appears in Weeks 12–13 and Week 16.

# Annex B — Document set

| ID | Document | When used |
| --- | --- | --- |
| ISF-INC-2026-001 | This Inception Report | M1 |
| ISF-SRS-2026-001 | Software Requirements Specification | Design/verification |
| ISF-UAT-2026-001 | UAT Test Pack (Excel) | Validation M3/M5 |
| rtm.csv | Requirement Traceability Matrix | STLC |
| Lab reports 1–7 | Formative evidence | Continuous |